## Cover Page
<Project Name>
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
Name
Role
Signature
Date
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Product Backlog E-Commerce Website Project ID: CSDINTADM22DF002 - POD1 C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
ECW1 | User Registration | End User | The user should be able to Register himself | The user would require to fill all the required information and then that data will be stored in the database
ECW2 | User Login | End User | The user should be able to sign in using his correct credentials | The user would require to enter correct credentials to log in himself into the web application
ECW3 | Home Page | End User | The user should be able to view the home page of the website regardless of signing in | The user would be able to surf through the home page of the web application regardless of signing into the web application
ECW4 | View Categories | End User | The user should be able to view different categories on the website to choose from | The user would be able to traverse through the different categories on the website
ECW5 | Searching | End User | The user should be able to search products on the website | The user would be able to search products of his choosing on the web application
ECW5 | Filtering | End User | The user should be able to filter out products based on various parameters | The user would be able to filter out products based on his preferences
ECW6 | Sorting | End User | The user should be able to sort the products based on various parameters | The user would be able to sort out products based on his preferences
ECW7 | Add Products without the need of signing in | End User | The user should be able to add products into the cart without signing in | The user would be able to add products into the cart for buying without the requirement of signing in
ECW8 | Add Products with signing in | End User | The user should be able to add products into the cart | The user would be able to add products into the cart for buying
ECW9 | View Products in cart | End User | The user should be able to view the added products in the cart | The user would be able to view the products in the cart selected for buying
ECW10 | Remove products from cart | End User | The user should be able to remove the added products from the cart | The user would be able to remove the products added in the cart
ECW11 | Payment | End User | The user should be able to pay for the products using UPI and COD | The user would be abe to pay using the available payment options and the bill will be generated thereafter
ECW12 | Tracking | End User | The user should be able to track down their product after successful payment | The user would be able to track their shipment and know the status of their delivery
ECW13 | Feedback and Rating | End User | The user should be able to provide feedback and rating after the successful delivery of the product | The user would be able to give a feedback message on the delivery process and the product and also be able to give star rating for the same
ECW14 | Replacement | End User | The user should be able to apply for replacement of the product | The user would be able to apply for replacement if the product satisfies the replacement conditions
ECW15 | Discount based on purchase history | End User | The user should be offered with discount based on his/her purchase history | The user would be able to avail the discount coupons/vouchers if they have purchased lot of products from this website in the past
ECW16 | Suggestions/Contact Us | End User | The user should be able to send suggestions on improving various parameters regarding the website, delivery, etc. | The user would be able to contact us via E-mail
ECW17 | Vendor Registration | Vendor | The vendor should be able to Register himself | The vendor would require to fill all the required information and then that data will be stored in the database
ECW18 | Vendor Login | Vendor | The vendor should be able to sign in using his correct credentials | The vendor would require to enter correct credentials to log in himself into the web application
ECW19 | Update Products | Vendor | The vendor should be able to update the number of products added in the website | The vendor would be able to increase and decrease the number of products put in for sale depending upon his preferences
ECW20 | Add Products | Vendor | The vendor should be able to add new products to sell in the website | The vendor would be able to add new items/products to sell in the web application
ECW21 | View Feedback | Vendor | The vendor should be able to view feedback of his products provided by the customers | The vendor would be able to see the feedback and star rating provided by the customer to his products

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000